## 219.1-5.6
Report No.： QSHEMS-R-OT-007
Customer：DBP |  |  | TANAMI GAS PIPELINE | [28 empty] | Pipe size：219.1*5.6mm
Start Date:10 Dec 2017 | [31 empty] | Coating structure： 3LPE
日期Date | 接收光管 Received bare pipe |  | 外涂3LPE External coated pipe | [10 empty] | 内涂Liquid Epoxylnternal coated pipe | [10 empty] | 试验管Test Pipe for Cutting Ring | [6 empty] | 管端重新切斜Re-beveling |  | 发运成品管 Delivery coated pipe
| 数量 Count pcs. | 长度 Length m | 总防腐 Total coated pipe pcs. | 当班合格Acceptable coated pipe pcs. | 目标合格支数Target pcs | 合格长度 Length of acceptable coated pipe m | 目标合格长度 Target Length m | 修补支数Repaired pipe pcs. | 光管隔离数量Quarantined bare pipe pcs. | 光管隔离管修磨Quarantined bare pipe treated pcs. | 光管隔离管切管Quarantined bare pipe cutted pcs | 涂层管废管数量Rejected coated pipe pcs. | 涂层管废管处理 Strip rejected coated pipe pcs. | 总防腐 Total coated pipe pcs. | 当班合格Acceptable coated pipe pcs. | 目标合格支数Target pcs | 合格长度 Length of acceptable coated pipe m | 目标合格长度 Target Length m | 修补支数Repaired pipe pcs. | 光管隔离数量Quarantined bare pipe pcs. | 光管隔离管修磨Quarantined bare pipe treated pcs. | 光管隔离管切管Quarantined bare pipe cutted pcs | 涂层管废管数量Rejected coated pipe pcs. | 涂层管废管处理 Strip rejected coated pipe pcs. | 白班 Day Shift |  |  | 夜班 Night Shift |  |  | 试验管数量 Test pipe pcs | 需切斜管数量 Re-bevel needed pcs | 管端切斜合格 Accept Re-bevel pcs | 数量 Count pcs | 长度 Length m
[25 empty] | 试验管 Test Pipe No. | 原始长度 Original Length m | 切样长度 Cutting Length m | 试验管 Test Pipe No. | 原始长度Original Length m | 切样长度 Cutting Length m
2018-02-03 | 161 | 2931.166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-02-04 | 170 | 3094.974 | 88 | 87 | 150 | 1598.93 | 2700 | 0 | 0 | 0 | 0 | 1 | 0 | [11 empty] | 1661270 | 15.21 | 0.8 | N/A | 0 | 0 | 1 | 0 | 0 | 0 | 0
2018-02-05 | 3 | 34.5 | 148 | 143 | 150 | 2608.01 | 2700 | 0 | 0 | 0 | 0 | 5 | 0 | [11 empty] | 1661550 | 17.87 | 0.8 | N/A | 0 | 0 | 1 | 0 | 0 | 0 | 0
2018-02-06 | 0 | 0 | 86 | 86 | 98 | 1547.42 | 1764 | 3 | 0 | 0 | 0 | 1 | 0 | [11 empty] | 1661620 | 17.47 | 0.2 | N/A | 0 | 0 | 1 | 0 | 0 | 0 | 0
2018-02-07 | 0 | 0 | 18 | 18 | 18 | 306.31 | 324 | 0 | 0 | 0 | 0 |  | 0 | [11 empty] | 1661150 | 17.87 | 0.2 | N/A | 0 | 0 | 1 | 0 | 0 | 0 | 0
2018-03-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | N/A | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 3 | 34.53
工程累计 Total project | 334 | 6060.64 | 340 | 334 | 416 | 6058.67 | 7488 | 3 | 0 | 0 | 0 | 7 | 0 | [11 empty] | N/A | 68.42 | 2 | N/A | 0 | 0 | 4 | 0 | 0 | 3 | 34.53
Note on E10: William:1659590 FBE layer more thick

## 219.1-7.0
Report No.： QSHEMS-R-OT-007
Customer：DBP |  |  | TANAMI GAS PIPELINE | [28 empty] | Pipe size：219.1*7.0mm
Start Date:10 Dec 2017 | [31 empty] | Coating structure： 3LPE
日期Date | 接收光管 Received bare pipe |  | 外涂3LPE External coated pipe | [10 empty] | 内涂Liquid Epoxylnternal coated pipe | [10 empty] | 试验管Test Pipe for Cutting Ring | [6 empty] | 管端重新切斜Re-beveling |  | 发运成品管 Delivery coated pipe
| 数量 Count pcs. | 长度 Length m | 总防腐 Total coated pipe pcs. | 当班合格Acceptable coated pipe pcs. | 目标合格支数Target pcs | 合格长度 Length of acceptable coated pipe m | 目标合格长度 Target Length m | 修补支数Repaired pipe pcs. | 光管隔离数量Quarantined bare pipe pcs. | 光管隔离管修磨Quarantined bare pipe treated pcs. | 光管隔离管切管Quarantined bare pipe cutted pcs | 涂层管废管数量Rejected coated pipe pcs. | 涂层管废管处理 Strip rejected coated pipe pcs. | 总防腐 Total coated pipe pcs. | 当班合格Acceptable coated pipe pcs. | 目标合格支数Target pcs | 合格长度 Length of acceptable coated pipe m | 目标合格长度 Target Length m | 修补支数Repaired pipe pcs. | 光管隔离数量Quarantined bare pipe pcs. | 光管隔离管修磨Quarantined bare pipe treated pcs. | 光管隔离管切管Quarantined bare pipe cutted pcs | 涂层管废管数量Rejected coated pipe pcs. | 涂层管废管处理 Strip rejected coated pipe pcs. | 白班 Day Shift |  |  | 夜班 Night Shift |  |  | 试验管数量 Test pipe pcs | 需切斜管数量 Re-bevel needed pcs | 管端切斜合格 Accept Re-bevel pcs | 数量 Count pcs | 长度 Length m
[25 empty] | 试验管 Test Pipe No. | 原始长度 Original Length m | 切样长度 Cutting Length m | 试验管 Test Pipe No. | 原始长度Original Length m | 切样长度 Cutting Length m
2018-02-03 | 161 | 2931.166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-02-04 | 170 | 3094.974 | 88 | 87 | 150 | 1598.93 | 2700 | 0 | 0 | 0 | 0 | 1 | 0 | [11 empty] | 1661270 | 15.21 | 0.8 | N/A | 0 | 0 | 1 | 0 | 0 | 0 | 0
2018-02-05 | 3 | 34.5 | 148 | 143 | 150 | 2608.01 | 2700 | 0 | 0 | 0 | 0 | 5 | 0 | [11 empty] | 1661550 | 17.87 | 0.8 | N/A | 0 | 0 | 1 | 0 | 0 | 0 | 0
2018-02-06 | 0 | 0 | 86 | 86 | 98 | 1547.42 | 1764 | 3 | 0 | 0 | 0 | 1 | 0 | [11 empty] | 1661620 | 17.47 | 0.2 | N/A | 0 | 0 | 1 | 0 | 0 | 0 | 0
2018-02-07 | 0 | 0 | 18 | 18 | 18 | 306.31 | 324 | 0 | 0 | 0 | 0 |  | 0 | [11 empty] | 1661150 | 17.87 | 0.2 | N/A | 0 | 0 | 1 | 0 | 0 | 0 | 0
2018-03-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | N/A | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 3 | 34.53
工程累计 Total project | 334 | 6060.64 | 340 | 334 | 416 | 6058.67 | 7488 | 3 | 0 | 0 | 0 | 7 | 0 | [11 empty] | N/A | 68.42 | 2 | N/A | 0 | 0 | 4 | 0 | 0 | 3 | 34.53
Note on E10: William:1659590 FBE layer more thick